## Slide 1
SCRUM & SPRINT WORKFLOW
How We Work at CitrusBit
An overview of our Scrum framework, sprint cycle, Jira workflow, and QA process
Prepared for supervisor walkthrough

## Slide 2
What Is Scrum?
A way of organizing Agile teamwork into short, repeating cycles
S
Definition
Scrum is an Agile framework that breaks a big project into small, fixed-length cycles called Sprints — usually 2 weeks. Each sprint delivers a working piece of the product, so progress is visible every two weeks instead of once at the end.
Why it matters: mistakes cost 2 weeks, not 2 years. Teams adjust direction constantly instead of discovering problems at the very end.
Waterfall vs. Scrum
Delivery
One big launch at the end
Every 2 weeks
Feedback
Only after everything's built
Continuous, each sprint
Risk
High — errors found late
Low — caught early
Change
Locked in from day one
Expected & welcomed
Scrum & Sprint Workflow
2

## Slide 3
The Three Scrum Roles
No bosses — just three clear jobs that keep the team moving
PO
Product Owner
The Visionary
Talks to clients & users, builds the master to-do list (Product Backlog), and decides what gets built first. And grooming of the User requirement
SM
Scrum Master
The Shield
Doesn't write code. Protects the team from distractions and clears roadblocks so work keeps flowing.
DEV
Developers
The Creators
Designers, engineers & testers who actually build, test, and deliver the working software each sprint.
Scrum & Sprint Workflow
3

## Slide 4
Scrum Artifacts & The Sprint Loop
Three tools the team tracks, moving in one continuous loop
Product
Backlog
Master wish-list
Sprint
Backlog
2-week promise
Sprint Work
(Scrum Team)
Build & Daily Scrum
Increment
Finished feature
Retrospective feedback loops back into the next Sprint Planning
Product Backlog
The full master list of every new feature and idea — ranked by the Product Owner.
Sprint Backlog
One of the feature or idea is pulled from Backlog and team commits to finish it.
Increment
The actual working result at sprint end — a real, tested, usable piece of the product.
Scrum & Sprint Workflow
4

## Slide 5
The CitrusBit 2-Week Sprint
Exactly what happens from Day 1 to Day 10
Day 1
Sprint Planning
2-4 hrs. Pull tasks from Product Backlog, estimate effort, tag Must-Have / Good-to-Have / Optional.
Day 2-8
Daily Work & Standups
15-min daily standup. 7 hrs/day expected effort (35 hrs/week). Work logged in Jira.
Day 5
Mid-Sprint Check-in
Optional 30-min review to confirm the team is on track.
Day 9
Readying for QA
Dev work wraps up early and hands off to QA — testing isn't crammed into the last day.
Day 10
Review + Retrospective
1-hr Sprint Review (demo) + 30-min Retrospective (what to improve).
Scrum & Sprint Workflow
5

## Slide 6
The Daily Standup
A 15-minute daily sync — same three questions, every morning
1
What did I do yesterday?
2
What will I do today?
3
Is anything blocking me?
Work Norms at CitrusBit
Expected productivity: 7 hours/day — 35 hrs/week, ~70 hrs per sprint
All work is logged daily in Jira so progress stays visible
Dev handoff to QA happens on Day 9 — never crammed into the last day
No Jira tickets for meetings, training, or admin — only real dev/deploy work
Scrum & Sprint Workflow
6

## Slide 7
Our Jira Board
Every task is a digital card (“ticket”) that moves left to right
To Do
Ticket 1
Ticket 2
Ticket 3
In Progress
Ticket 1
Ticket 2
In Review / Testing
Ticket 1
Ticket 2
Done
Ticket 1
Ticket 2
Ticket 3
Popular tools: Jira · Trello · Asana — CitrusBit runs on Jira
Scrum & Sprint Workflow
7

## Slide 8
Jira Ticket Types
Every ticket in Jira is called an “Issue” — and always belongs to an Epic
●
Epic
A large feature/category that groups smaller tickets. Every task must belong to one.
●
User Story
Written as: As a [user], I want to [action], so that [benefit].
●
Enhancement
Technical, behind-the-scenes work (e.g. setting up a database).
●
Bug
A problem or mistake in the existing system.
●
Change Request
A brand-new feature not in the original plan — usually billed extra.
●
Test Issue
A bug QA finds mid-sprint. Zero hours estimated — doesn't count as unplanned work.
Scrum & Sprint Workflow
8

## Slide 9
QA & Testing Strategy
~15-20% of every sprint's effort is dedicated to quality assurance
15-20%
of sprint effort
reserved for QA
Load Testing
Apache JMeter simulates thousands of concurrent users to make sure servers hold up.
Regression Testing
Old features are re-tested to confirm new code hasn't broken what already worked.
Automated Code Review
SonarQube scans code on the last day of the sprint for security flaws and messy code.
Scrum & Sprint Workflow
10

## Slide 10
Security & IP Protection
How CitrusBit protects client code, data, and payments
✓
Private Code
All code lives in paid, private GitHub repositories — never public.
✓
No Local Data
Client databases and sales data stay on secure AWS servers, never copied to personal clouds.
✓
No Stored Cards
Card details are never stored — payments pass securely through Stripe or Braintree.
Scrum & Sprint Workflow
11

## Slide 11
Key Takeaways
We work in 2-week Sprints — planned Day 1, reviewed Day 10
Three roles keep it running: Product Owner, Scrum Master, Developers
Every task is a Jira ticket, tagged under an Epic, moved To Do → Done
QA gets 15-20% of every sprint, with load, regression & code-review checks
Security is built in: private repos, AWS-only data, no stored card details
Thank you
12